## Tsts and Test Case Ids
Comtrac_All:
252752 or 281841 or 281839 or 281838 or 281840 or 281842 or 281843 or 284080 or 284084 or 284083 or 284082 or 284085 or 253158 or 255887 or 294945 or 306098 or 306099 or 256566
CustomerMoves:
261711 or 261713 or 277336 or 277337 or 283871 or 261710 or 261709 or 261708
DTA:
303883 or 304112 or 303214 or 303982 or 303219 or 303218 or 306459
MPC:
303396 or 303401 or 303318 or 303340 or 303341 or 303397 or 303402 or 303453 or 303398 or 302670 or 303400 or 303394 or 303393 or 303442 or 303452 or 303395
SwivelCSG:
305113 or 305125 or 305114 or 267957 or 263795 or 263794 or 263793 or 302667 or 302672 or 302668 or 255885 or 267955 or 267956 or 304008 or 280139 or 279713 or 277552 or 280138 or 277545 or 277549 or 282905 or 282906 or 306095 or 306094 or 302664 or 302666 or 258581 or 264014 or 284288 or 301976 or 304010 or 302051 or 287365 or 287366 or 287708 or 284075 or 277554 or 282062 or 277548 or 303886 or 304013 or 277553 or 301971 or 301770 or 303880 or 303881 or 280707 or 277558 or 277559 or 277561 or 277543 or 279707 or 301771 or 282904 or 277544 or 297772
Dotcom:
255876 or 256424 or 256434 or 255875 or 255877 or 301398 or 288798 or 301772 or 303319 or 303317 or 264015 or 295002 or 301181 or 294946 or 260695 or 252749 or 301399 or 301400 or 302859 or 301401 or 301402 or 301488 or 301504 or 255874 or 255878 or 256561 or 263432 or 256562 or 287357 or 256431 or 287355 or 252748 or 306101 or 299289 or 299288 or 306100 or 285500 or 285502 or 256432 or 255872 or 256425 or 256433 or 264420 or 264419 or 287353 or 264421 or 258582 or 258867 or 283301 or 287352 or 283300 or 283299 or 283292 or 283291 or 283295 or 256568
SIK-Negative Scenarios:
277898 or 256567 or 277903 or 256565 or 303654 or 295266 or 296227 or 295259 or 260694 or 260712 or 260693 or 299310 or 295260 or 301503 or 287493 or 260696 or 260692 or 306228 or 287358 or 295275 or 295280 or 288619 or 296228 or 299308 or 299309 or 299311 or 299325 or 299312 or 301764 or 263734 or 301553
Hav Market:
287474 or 287476 or 287473 or 287478 or 287480
DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight:
287451 or 288328 or 286937 or 293478 or 288325 or 286949 or 286942 or 287660 or 286950 or 295604 or 286924 or 286938 or 286943 or 286947 or 287680 or 295923 or 295610 or 295619 or 295613 or 293330 or 293334 or 287655 or 287659 or 287662 or 286927 or 286939 or 286944 or 286949 or 295609 or 287677 or 288326 or 295008 or 293304 or 293303 or 293317 or 293302 or 293302 or 295614 or 296229 or 295746 or 286940 or 295009 or 295010 or 287653 or 287657 or 287661 or 287654 or 287658 or 287663 or 286941 or 286946 or 295618 or 288327 or 289074 or 287674 or 289075 or 293320 or 293323 or 295007 or 295151 or 295477 or 295605 or 295608 or 295615 or 296230 or 299058 or 307670 or 307682 or 307676 or 307957 or 307960 or 307964 or 307672 or 307958 or 307961 or 307963 or 307671 or 307673 or 306389 or 307055 or 307057 or 307056 or 307058 or 306984 or 306998 or 306949 or 306390 or 306394 or 306395 or 306985 or 306999 or 306950 or 306951
RTP Upgrade/Downgrade:
287035 or 287038 or 287041 or 287043 or 287028 or 287030 or 287034 or 295629 or 294717 or 295627 or 293414 or 287039 or 287040 or 287042 or 287027 or 287024 or 287031 or 287032 or 287033 or 287036 or 287037 or 295625 or 295626 or 295628 or 287707 or 295012 or 295013 or 295620 or 287056 or 287706 or 287704 or 295011 or 295622 or 295623 or 295624 or 295621 or 296465 or 299061 or 299060 or 307688 or 307689 or 307661
Handle Invalid Services:
302444 or 302582 or 302484 or 302471 or 302451 or 302455 or 302453 or 302483 or 302446 or 302454 or 302442 or 302462 or 302452
RTP_Normal Scenarios:
294811 or 298456 or 298457 or 298458 or 300673 or 300669 or 300723 or 300665 or 300668 or 300670 or 300671 or 300672 or 300674 or 300675 or 296443 or 296467 or 287556 or 286978 or 286986 or 287625 or 287634 or 287649 or 286995 or 286985 or 287051 or 288322 or 287005 or 287647 or 287048 or 286974 or 287559 or 287626 or 288321 or 287650 or 287619 or 286987 or 287044 or 287630 or 287644 or 287652 or 287620 or 287651 or 286952 or 286972 or 286994 or 287004 or 287646 or 300961 or 300965 or 300966 or 293398 or 293405 or 293400 or 293354 or 293355 or 293412 or 302160 or 296823 or 287460 or 286984 or 286975 or 287623 or 287632 or 287014 or 287557 or 286979 or 286973 or 286996 or 287006 or 287648 or 288323 or 287052 or 286980 or 286997 or 287642 or 300964 or 295022 or 287045 or 286975 or 286998 or 287636 or 295473 or 287462 or 286977 or 300962 or 287624 or 287633 or 300963 or 296826 or 300964 or 287728 or 287729 or 287730 or 287731 or 287732 or 289078 or 287645 or 294012 or 294691 or 294065 or 287643 or 293487 or 286976 or 295930 or 295925 or 295939 or 295938 or 295940 or 301131 or 286919 or 295747 or 295800 or 294869 or 286948 or 286945 or 296461 or 296466 or 295801 or 289081 or 294062 or 295515 or 289080 or 294061 or 294731 or 295926 or 295918 or 303040 or 303041 or 303042 or 303043 or 303045 or 303047 or 303048 or 303049 or 303050 or 303052 or 307642 or 307775 or 307968 or 308036 or 307976 or 308087 or 307783 or 307780 or 307965 or 307971 or 307975 or 307645 or 308035 or 307969 or 308088 or 307648 or 308089 or 308090 or 308091 or 307644 or 307773 or 307967 or 307973 or 307977 or 307650 or 307781 or 307966 or 307970 or 307974 or 307649 or 306382 or 307070 or 307073 or 306968 or 306943 or 306385 or 306388 or 306990 or 306945 or 307051 or 307052 or 308707 or 307444 or 307053 or 308706 or 308705 or 307054 or 307074 or 306992 or 307075 or 308704 or 306382 or 306970 or 308735 or 306384 or 307071 or 307072 or 306969 or 306944 or 306991 or 307069 or 306946 or 306947
30Day_Disconnect_All:
287078 or 287079 or 287084 or 287085 or 287086 or 287087 or 284402 or 284403 or 287073 or 284405 or 296835 or 296841 or 287083 or 284415 or 284407 or 287070 or 284406 or 287092 or 287093 or 287094 or 287095 or 284414 or 287074 or 284413 or 284497 or 284408 or 293384 or 295014 or 287115 or 287103 or 287099 or 302152 or 302158 or 302153 or 304773 or 298238 or 302147 or 302388 or 302150 or 295929 or 302584 or 295469 or 295492 or 295460 or 295465 or 295468 or 295466 or 295467 or 295464 or 295491 or 300556 or 300557 or 300558 or 300559 or 300552 or 300553 or 300554 or 300555 or 300792 or 300793 or 297307 or 297306 or 304174 or 304176 or 296816 or 296818 or 297306 or 294708 or 294699 or 294697 or 294694 or 294693 or 297306 or 304177 or 304175 or 304178 or 294822 or 288865 or 294733 or 297438 or 302157 or 307699 or 307652 or 307651 or 307654 or 308690 or 308687 or 308685 or 308686 or 308688 or 308684 or 308689 or 295461 or 295462 or 295463 or 284404 or 298237
Handle Invalid with Virtualize:
302466 or 302473 or 302464 or 302482 or 302478 or 302583 or 302474 or 302471 or 302465 or 302470 or 302450 or 302451 or 302477 or 295469 or 302488 or 295492 or 295491 or 302489
IgnoreWorklistRTP:
294815 or 294816 or 294817 or 294818 or 294819 or 294815 or 294816 or 294818 or 294819 or 294817 or 302674 or 302675 or 302676 or 302677 or 302678 or 302679 or 302680 or 302681 or 302682 or 302683 or 302684 or 302685 or 302686 or 302687 or 302688 or 302689 or 302690 or 302691 or 302692 or 302693 or 302694 or 302695 or 302696 or 302697 or 302698 or 302699 or 302700 or 302701 or 302702 or 302703 or 302704 or 302705 or 302706 or 302707 or 302708 or 302709 or 302710 or 302711 or 302712 or 302713 or 302714 or 302715 or 302716 or 302717 or 302718 or 302719 or 302720 or 302721 or 302722 or 302723 or 302731 or 302732 or 302733 or 302734 or 302735 or 302736 or 302737 or 302738 or 302739 or 302740 or 302741 or 302742 or 302743 or 302744 or 302745 or 302746 or 302747 or 302748 or 302749 or 302750 or 302751 or 302752 or 302753 or 302754 or 302755 or 302756 or 302757 or 302758 or 302759 or 302760 or 302761 or 302762 or 302763 or 302764 or 302765 or 302766 or 302767 or 302768 or 302769 or 302770 or 302771 or 302772 or 302773 or 302774 or 302775 or 302776 or 302777 or 302778 or 302779 or 302780 or 302781 or 302782 or 302783 or 302784 or 302785 or 302786 or 302723 or 302724 or 302725 or 302726 or 302727 or 302728 or 301120 or 302729
Release From Thirty Day All:
299123 or 299125 or 299127 or 299124 or 299126 or 299128 or 299124 or 299126 or 299128 or 297300 or 297640 or 294523 or 294527 or 297639 or 297299 or 294524 or 294525 or 294529
Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check:
302471 or 302473 or 302474 or 302476 or 302477 or 302436 or 302419 or 302406 or 302413 or 302421 or 302417 or 302425 or 302408 or 302423 or 302410 or 302414 or 302406 or 302436 or 301115 or 301116 or 301119 or 302427 or 302430 or 302431 or 302432 or 302433 or 294832 or 294834 or 294835 or 294837 or 294839 or 301112 or 301113 or 295174 or 295175 or 295176 or 301117 or 295178 or 295922 or 295172 or 295173 or 301114 or 301118
JasperAfterCOS_ResumeFlowAddition:
295017 or 295313 or 295513 or 295316 or 295320 or 296819 or 295319 or 295318 or 296825 or 296845 or 296824 or 295177 or 295317 or 295018 or 296843 or 301149 or 301136 or 301127 or 301128 or 301150 or 301151 or 301153 or 301126 or 301148 or 301130 or 301133 or 301134 or 301137 or 301143
Cancel_ON_Disconnect:
288892 or 288860 or 288867 or 288893 or 288868 or 288894 or 287015 or 288897 or 287016 or 294820 or 288891 or 288866 or 294004 or 294673 or 294692 or 293445 or 294674 or 294681 or 294675 or 294683 or 294682 or 294685 or 293449 or 294678 or 287017 or 287018 or 287021 or 294706 or 288869 or 294704 or 294703 or 288862 or 288886 or 288732 or 288733 or 288734 or 288896 or 288884 or 288885 or 293444 or 288861 or 288887 or 294821 or 294735 or 294076 or 294701 or 293504 or 294078 or 289077 or 307653 or 307684 or 307685 or 307687
SCHEDULE_UPGRADE_DOWNGRADE:
295487 or 301489 or 301578 or 301577 or 301574 or 294718 or 295488 or 301491 or 302106 or 301889 or 301500 or 302794 or 303222 or 303230 or 303223 or 301490 or 301888 or 301494 or 302793 or 303246 or 303262 or 302789 or 294720 or 294720 or 301498 or 301496 or 307044 or 307046 or 307043 or 307045 or 307042 or 307041 or 307028 or 307031 or 307033 or 307035 or 307029 or 307030 or 307032 or 307034 or 307040 or 310157 or 308672 or 307664 or 307978 or 307663 or 308311 or 308310 or 307691 or 310156 or 308673

## Nov6
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | #DIV/0!
2 | Comtrac_All | Ramya | #DIV/0!
3 | CustomerMoves | Bhuvana | #DIV/0!
4 | DTA | Ramya | #DIV/0!
5 | SwivelCSG | Ashwini | #DIV/0!
6 | DOTCOM | Yamini | #DIV/0!
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 35.94% | 64 | 23 | 37 | 4 | 163 | A4 | All 37 are due to account clean up failure issue | changed account number for both CSG and DDP
8 | RTP Normal Scenarios | Ramya | 28.03% | 132 | 37 | 93 | 2 | 317 | A4 | 30- COS issue,63 -latency issue
9 | Handle_Invalidservices | Ashwini | 61.54% | 13 | 8 | 5 | 0 | 160 | A4 | 5 - COS issue | NA
10 | Release_From_ThirtyDay_All | Yamini | 55.56% | 27 | 15 | 8 | 4 | 499 | A4 | No run -4 test case update ALM positive failed due to connection issue 2 test case -entries are not present in oracle database 2 test case- edit terminal no response(HS-JS-; nested exception is: java.net.SocketException: Connection reset 2 test case- COPS error | changed status to ACTIVE and after disconnect status to new and ready for activation.
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 89.29% | 28 | 25 | 2 | 1 | 59 | A5 | 2- Latency issue
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 75.86% | 29 | 22 | 7 | 0 | 43 | A5 | 7 - COS issue | NA
13 | Cancel_ON_Disconnect | Ashwini | 100% | 49 | 49 | 0 | 0 | 78 | A5
14 | Handle_Invalid Services with Virtualize | Ashwini | 75.86% | 29 | 22 | 7 | 0 | 95 | A5 | COS issue
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 100% | 25 | 25 | 0 | 0 | 34 | A5
16 | RTP_Upgrade and downgrade | Bhuvana | 84.62% | 39 | 33 | 6 | 0 | 228 | A5 | 287034,294717,287039,287040 - Create Account no response 287704 - Process home security failure 299061 - get account no response(data present in mysql table)
17 | 30Day Disconnect | Yamini | 73.42% | 79 | 58 | 17 | 4 | 194 | A5 | transfer indicator 300552 - Process home security failure 300553,300554 -get account failure ICC ID: 2 failed due to get account failure not able to identify reason for No run , CSG- 3 failed - COS failure DDP- 4 failed- Add account group and remove account group failed
18 | IgnoreworklistRTP | Yamini | 93.22% | 118 | 110 | 0 | 8 | 61 | A2 | no error in report, unable to identify no run issue.

## Nov9
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | #DIV/0!
2 | Comtrac_All | Ramya | #DIV/0!
3 | CustomerMoves | Bhuvana | #DIV/0!
4 | DTA | Ramya | #DIV/0!
5 | SwivelCSG | Ashwini | #DIV/0!
6 | DOTCOM | Yamini | #DIV/0!
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 29.69% | 64 | 19 | 45 | 0 | 150 | A2 | 25 test cases-Account Number Issue,20-COS Issue | We cancelled all the account numbers manually and we made all account numbers proper
8 | RTP Normal Scenarios | Ramya | 80.3% | 132 | 106 | 26 | 0 | 387 | A2 | 22-COS issue, 2 - Cz 2 DDS triggered one for install and one for CVR. So DDS validation failed | NA
9 | Handle_Invalidservices | Ashwini | 61.54% | 13 | 8 | 5 | 0 | 156 | A2 | 5 test case-due to COS Issue | NA
10 | Release_From_ThirtyDay_All | Yamini | 55.56% | 27 | 15 | 11 | 1 | 453 | A2 | 1 test case- No Run due to connection issue thrown error as " unexpected end of file from server" 2 test case- cops no response 9 test case- Latency Issue | NA
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 89.29% | 28 | 25 | 3 | 0 | 57 | A4 | 3 test cases- Latency Issue | NA
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 82.76% | 29 | 24 | 5 | 0 | 45 | A4 | 5- COS scenarios | NA
13 | Cancel_ON_Disconnect | Ashwini | 100% | 49 | 49 | 0 | 0 | 77 | A4
14 | Handle_Invalid Services with Virtualize | Ashwini | 65.52% | 29 | 19 | 10 | 0 | 95 | A4 | 10-COS Issue | NA
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 20% | 25 | 5 | 20 | 0 | 35 | A4 | It went to direct upgrade and downgrade | NA
16 | RTP_Upgrade and downgrade | Bhuvana | 82.05% | 39 | 32 | 7 | 0 | 229 | A4 | RJ Error - Cancel was not proper. | We cancelled all the account numbers manually and we made all account numbers proper
17 | 30Day Disconnect | Yamini | 41.77% | 79 | 33 | 42 | 4 | 190 | A4 | 10 test cases- due to COS issue 12 test cases-due to latency issue Remaining test cases due to getAccount no response 4 test cases-We couldn’t found any error exception regarding update ALM in reports , so we are not able to find reason | NA
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 49 | A5

## Nov11
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | 100% | 12 | 12 | 0 | 0 |  | A5
2 | Comtrac_All | Ramya | 62.5% | 16 | 10 | 5 | 1 |  | A5 | Address validation failure
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 |  | A5
4 | DTA | Ramya | 0% | 6 | 0 | 6 | 0 |  | A5 | Flow stopped in getlocation | Changed Account numbers , need to monitor
5 | SwivelCSG | Ashwini | 100% | 54 | 54 | 0 | 0 |  | A5
6 | DOTCOM | Yamini | 100% | 54 | 54 | 0 | 0 |  | A5
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 95.31% | 64 | 61 | 3 | 0 | 150 | A2 | Index out of range error
8 | RTP Normal Scenarios | Ramya | 0% | 148 | 0 | 0 | 148 | 387 | A2 | Dint run
9 | Handle_Invalidservices | Ashwini | 76.92% | 13 | 10 | 3 | 0 | 156 | A2 | Cops,DDS no response | NA
10 | Release_From_ThirtyDay_All | Yamini | 62.96% | 27 | 17 | 10 | 0 | 453 | A2 | Process got truncated inbetween. So data base validations failed | Not sure how process got truncated in between going forwad we are monitoring this also . If this is not resolved we have a plan to keep suspended script in b/w tst files
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 85.71% | 28 | 24 | 4 | 0 | 57 | A4 | Latency issue | NA
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 82.76% | 29 | 24 | 5 | 0 | 45 | A4 | Account already exists from COPS | Changed Account number
13 | Cancel_ON_Disconnect | Ashwini | 80% | 50 | 40 | 9 | 1 | 77 | A4 | DDS no response-2, COPS no response-7 | NA
14 | Handle_Invalid Services with Virtualize | Ashwini | 79.31% | 29 | 23 | 6 | 0 | 95 | A4 | Cops,DDS no response | NA
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 96% | 25 | 24 | 1 | 0 | 35 | A4 | Status in Schedule table was Open. Script was looking for completed | Latency issue
16 | RTP_Upgrade and downgrade | Bhuvana | 89.74% | 39 | 35 | 4 | 0 | 229 | A4 | Latency issue | NA
17 | 30Day Disconnect | Yamini | 67.09% | 79 | 53 | 23 | 3 | 190 | A4 | createCMS error-6,Environment slowness-2, Remaining scenarios getAcc no response which occurred inbetween process got truncated, So status of Thirtyday disconnect process became executing instead of suspended at the same time entries are getting updated in parasoft entry table so it leads to getAcc no response | Not sure how process got truncated in between going forwad we are monitoring this also . If this is not resolved we have a plan to keep suspended script in b/w tst files
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 49 | A5
| Total |  | 71% | 799 | 568 | 79 | 152

## Nov12
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | 100% | 12 | 12 | 0 | 0 |  | A5
2 | Comtrac_All | Ramya | 93.75% | 16 | 15 | 1 | 1 |  | A5 | Latency issue | Environment issue
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 |  | A5
4 | DTA | Ramya | 0% | 6 | 0 | 6 | 0 |  | A5 | Billing order id validation failed | Necessary Action has been taken
5 | SwivelCSG | Ashwini | 100% | 54 | 54 | 0 | 0 |  | A5
6 | DOTCOM | Yamini | 100% | 54 | 54 | 0 | 0 |  | A5
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 95.31% | 64 | 61 | 3 | 0 | 150 | A2 | Index out of range error | Java error need to check with Bhuvana
8 | RTP Normal Scenarios | Ramya | 92.57% | 148 | 137 | 11 | 0 | 387 | A2 | getAcc no response | Environment issue
9 | Handle_Invalidservices | Ashwini | 69.23% | 13 | 9 | 4 | 0 | 156 | A2 | Account already exists error from create Acc | Cancelled account numbers manually, need to monitor
10 | Release_From_ThirtyDay_All | Yamini | 51.85% | 27 | 14 | 12 | 1 | 453 | A2 | 4 scenarios getAccount no response in QA1, 1 CreateCMS error response , 3- Latency issue 3-Intermitent issue status changed to completed and cancelled instead of open,1 RJ error | Environment issue
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 96.43% | 28 | 27 | 1 | 0 | 57 | A4 | CreaCMS error response | Environment issue
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 89.66% | 29 | 26 | 3 | 0 | 45 | A4 | got CVR calls and hence script failed | Need to clear all CVR configurations before Running.
13 | Cancel_ON_Disconnect | Ashwini | 100% | 50 | 50 | 0 | 0 | 77 | A4 | NA | NA
14 | Handle_Invalid Services with Virtualize | Ashwini | 72.41% | 29 | 21 | 8 | 0 | 95 | A4 | Account already exists error from create Acc | Cancelled account numbers manually, need to monitor
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 32% | 25 | 8 | 17 | 0 | 35 | A4 | Date Validation failed | Necessary Action has been taken
16 | RTP_Upgrade and downgrade | Bhuvana | 97.44% | 39 | 38 | 1 | 0 | 229 | A4 | Latency issue | Environment issue
17 | 30Day Disconnect | Yamini | 67.09% | 79 | 53 | 22 | 4 | 190 | A4 | CreaCMS error response-4,DDs error resp-2, remaining scenarios failed due to latency issue where in we got null pointer exception in data base updation, No run-Update ALM null pointer exception | Environment issue
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 49 | A5
Note: Most of the failures are mainly due to Environment issue, We are observing Error response from createAccount and DDS “Conection reset error”

## Nov17
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | 100% | 10 | 10 | 0 | 0 | 20 | A5
2 | Comtrac_All | Ramya | 100% | 18 | 18 | 0 | 0 | 18 | A5
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 | 5 | A5
4 | DTA | Ramya | 100% | 6 | 6 | 0 | 0 | 22 | A5
5 | SwivelCSG | Ashwini | 74.55% | 55 | 41 | 14 | 0 | 29 | A5 | Account number issue. | Cleaned account number
6 | DOTCOM | Yamini | 90.74% | 54 | 49 | 5 | 0 | 124 | A5 | Environment Issue: Location service end point was down.
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 95.31% | 64 | 61 | 3 | 0 | 136 | A1 | String index out of bound exception. | Not able to identify root cause , we are not seeing any failure in response. We kicked off manually with these account number,we are not seeing any errors. Will monitor for some more days and find root cause.
8 | RTP Normal Scenarios | Ramya | 0% | 132 | 0 | 0 | 132 | 1 | A1 | Unsupported Excel spreadsheet format | File got corrupted. Modified XL sheet
9 | Handle_Invalidservices | Ashwini | 46.15% | 13 | 6 | 7 | 0 | 190 | A1 | Account already exists error from create Acc
10 | Release_From_ThirtyDay_All | Yamini | 77.78% | 27 | 21 | 5 | 1 | 579 | A4 | 2 scenarios- RJ error wherein it happened in between Disconnect and release from table 3-latency issue. 1No Run- update positive ALM with the error unexpected end of file server.
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 92.86% | 28 | 26 | 2 | 0 | 57 | A2 | CMS Account issue
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 100% | 29 | 29 | 0 | 0 | 45 | A2
13 | Cancel_ON_Disconnect | Ashwini | 100% | 49 | 49 | 0 | 0 | 79 | A2
14 | Handle_Invalid Services with Virtualize | Ashwini | 55.17% | 29 | 16 | 13 | 0 | 96 | A2 | HSS service was down.
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 100% | 25 | 25 | 0 | 0 | 35 | A2
16 | RTP_Upgrade and downgrade | Bhuvana | 97.44% | 39 | 38 | 1 | 0 | 230 | A2 | RJ error. | Modified account number.
17 | 30Day Disconnect | Yamini | 89.87% | 79 | 71 | 8 | 0 | 198 | A2 | 5 scenarios- CreateCMSAccount Id Issue. 2 scenario- latency issue 1-Process ran in between so, it went to no response
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 47 | A4
| Total |  | 75.61% | 783 | 592 | 58 | 133

## Nov20
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | 80% | 10 | 8 | 2 | 0 |  | A5 | orders were not cancelled properly | Cancelled order manually. | Blocked address match: 3188 MCCOLLEY RD,APT 188,MILFORD,DE,19963-4306. This address has been blocked by your Regional Risk Management team.
2 | Comtrac_All | Ramya | 100% | 18 | 18 | 0 | 0 |  | A5
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 |  | A5
4 | DTA | Ramya | 100% | 6 | 6 | 0 | 0 |  | A5
5 | SwivelCSG | Ashwini | 81.82% | 55 | 45 | 10 | 0 |  | A5 | D02 issue | sent email to development Team
6 | DOTCOM | Yamini | 92.59% | 54 | 50 | 4 | 0 |  | A5 | 4 scenarios- latency Issue Latency is around 4 min between getLocation and queryContract calls | NA
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 86.84% | 76 | 66 | 10 | 0 |  | A1 | Pointed to QA1 for xhs events and simulator was on during batch run | changed environment to DTDEV
8 | RTP Normal Scenarios | Ramya | 77.78% | 162 | 126 | 35 | 1 |  | A1 | Too many connection issue | NA
9 | Handle_Invalidservices | Ashwini | 76.92% | 13 | 10 | 3 | 0 |  | A1 | Too many connection issue
10 | Release_From_ThirtyDay_All | Yamini | 66.67% | 27 | 18 | 8 | 1 |  | A4 | 1 scenario- Latency Issue, before release from 30 day calls, Cancel request triggered so it went to Cancel instead of Disconnect (diff 48 sec) 4 scenario- Latency Issue (Approx. diff 4 mins) 1 scenario- Jasper No response 1 scenario- Latency issue-DDS processHomeSecurityInfo call- (15 sec difff) 1 scenario-Latency Issue- Null pointer Exception in 30 Day table 1 No Run- update Positive ALM Failed- unexpected end of file server. | NA
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 64.29% | 28 | 18 | 10 | 0 |  | A2 | 1 - latency issue 4 - createCMS Account Issue 5- "Too Many Connections error" | virtualizer issue
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 51.72% | 29 | 15 | 14 | 0 |  | A2 | Too many connection issue | Na
13 | Cancel_ON_Disconnect | Ashwini | 28.3% | 53 | 15 | 38 | 0 |  | A2 | Too many connection issue | Na
14 | Handle_Invalid Services with Virtualize | Ashwini | 58.62% | 29 | 17 | 12 | 0 |  | A2 | Too many connection issue | NA
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 4% | 25 | 1 | 24 | 0 |  | A2 | kicked off job on 21st and schedule date was not modified to current date, get account failure issue | modifed to current date. | Intrado failure intemittent issue
16 | RTP_Upgrade and downgrade | Bhuvana | 45.24% | 42 | 19 | 23 | 0 |  | A2 | Get Account response failure ,too many Connection failure issue | NA | Intrado failure intemittent issue
17 | 30Day Disconnect | Yamini | 30.12% | 83 | 25 | 57 | 1 |  | A2 | 58 Scenarios -Error- Too Many Connections error due to this getAccount went to no response | NA
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 |  | A4
| Total |  | 69.74% | 836 | 583 | 250 | 3
All 26 no run test cases has been taken care

## Nov25
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | 40% | 10 | 4 | 6 | 0 |  | A5 | Failure in submit order because of corp 99996 ( Blocked address match: 3188 MCCOLLEY RD,APT 188,MILFORD,DE,19963-4306. This address has been blocked by your Regional Risk Management team.) | email sent to DEV team
2 | Comtrac_All | Ramya | 88.89% | 18 | 16 | 2 | 0 |  | A5 | received "Disconnected Customer data is received for NEW Order" error | NA
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 |  | A5
4 | DTA | Ramya | 0% | 6 | 0 | 6 | 0 |  | A5
5 | SwivelCSG | Ashwini | 100% | 55 | 55 | 0 | 0 |  | A5
6 | DOTCOM | Yamini | 90.74% | 54 | 49 | 5 | 0 |  | A5 | Environment slowness which couldn,t cancel Order which leads to duplicate order id | NA
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 93.59% | 78 | 73 | 5 | 0 |  | A1 | String index out of bound exception even after modifying account number | created new sheet for DDP insight scenarios and checked in SVN
8 | RTP Normal Scenarios | Ramya | 95.06% | 162 | 154 | 8 | 0 |  | A1 | 2 install failed - Intrado no response,corresponding change of service, suspend restore failed. | NA
9 | Handle_Invalidservices | Ashwini | 55.56% | 18 | 10 | 8 | 0 |  | A1 | simulator was on it was running parallely with 30 day script | modified configuration in Jenkins to kick off Handle invalid services before 30 day disconnect in same job.
10 | Release_From_ThirtyDay_All | Yamini | 81.48% | 27 | 22 | 5 | 1 |  | A4 | Intrado failure | NA
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 64.29% | 28 | 18 | 10 | 0 |  | A2 | Intrado failure
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 100% | 29 | 29 | 0 | 0 |  | A2 | Too many connection issue | Na
13 | Cancel_ON_Disconnect | Ashwini | 90.74% | 54 | 49 | 5 | 0 |  | A2 | DDS error response during install hence second iteration failed intrado no response | Na
14 | Handle_Invalid Services with Virtualize | Ashwini | 12.5% | 24 | 3 | 3 | 18 |  | A2 | intrado no response ALM connection failure | NA
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 76% | 25 | 19 | 6 | 0 |  | A2 | due to intermittent intrado failure issue | NA
16 | RTP_Upgrade and downgrade | Bhuvana | 22.73% | 44 | 10 | 34 | 0 |  | A2 | responder Intrado failure | NA
17 | 30Day Disconnect | Yamini | 65.91% | 88 | 58 | 27 | 3 |  | A2 | Intrado failure | NA
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 |  | A4
| Total |  | 82.15% | 846 | 695 | 130 | 22
All 26 no run test cases has been taken care

## Dec2
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | How did we fix?
1 | Multiple_Product_Component | Bhuvana | 100% | 12 | 12 | 0 | 0 | 20 | A5
2 | Comtrac_All | Ramya | 100% | 18 | 18 | 0 | 0 | 19 | A5
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 | 5 | A5
4 | DTA | Ramya | 85.71% | 7 | 6 | 0 | 1 | 21 | A5 | 1 no -run because we didn’t move first name ,last name scenario to OCR
5 | SwivelCSG | Ashwini | 100% | 55 | 55 | 0 | 0 | 29 | A5
6 | DOTCOM | Yamini | 69.23% | 52 | 36 | 10 | 6 | 118 | A5 | 10 scenarios failed because of environment slowness 5 is in No run . Not sure RMA skipped off. | NA
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 94.74% | 76 | 72 | 4 | 0 | 157 | A1 | String index out of bound exception, only if we kick off via Jenkins (I,e while running all jobs parallely). Kicked off job again with only one tst via Jenkins and I am not facing this string index out of bound exception.
8 | RTP Normal Scenarios | Ramya | 96.91% | 162 | 157 | 5 | 0 | 398 | A1 | In between COS failed. Got Only Event call. So Suspend, restore ,Cancel failed | This is the first time we got this isuue. We will monitor this.
9 | Handle_Invalidservices | Ashwini | 84.62% | 13 | 11 | 2 | 0 | 189 | A2 | Environment slowness | NA
10 | Release_From_ThirtyDay_All | Yamini | 77.78% | 27 | 21 | 5 | 1 | 588 | A2 | 1 No Run - Update ALM Pass -unexpected end of file from server. 1 failed - Intermittent Issues:: Status updated as Completed instead of open. 4 failed - Environment slowness | NA
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 96.43% | 28 | 27 | 1 | 0 | 59 | A4 | 1 scenario failed -Environment slowness | NA
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 100% | 29 | 29 | 0 | 0 | 46 | A4
13 | Cancel_ON_Disconnect | Ashwini | 94.34% | 53 | 50 | 3 | 0 | 86 | A4 | Environment slowness | NA
14 | Handle_Invalid Services with Virtualize | Ashwini | 89.66% | 29 | 26 | 3 | 0 | 76 | A4 | Environment slowness | NA
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 100% | 23 | 23 | 0 | 0 | 36 | A4
16 | RTP_Upgrade and downgrade | Bhuvana | 69.05% | 42 | 29 | 13 | 0 | 239 | A4 | All 13 cases are due to Environment slowness | NA
17 | 30Day Disconnect | Yamini | 96.25% | 80 | 77 | 2 | 1 | 207 | A4 | Failed: 1 scenario- creatcmsaccount Issue 1 scenario- Null pointer exception in DB table whereas time differences between disconnect and update entries in table No run: 1 scenario-update positive alm null pointer exception. | We are following up CreateCMS Acount Issue.
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 79 | A2
| Total |  | 93.15% | 832 | 775 | 48 | 9

## Dec17
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run In ALM | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | #DIV/0!
2 | Comtrac_All | Ramya | #DIV/0!
3 | CustomerMoves | Bhuvana | #DIV/0!
4 | DTA | Ramya | #DIV/0!
5 | SwivelCSG | Ashwini | #DIV/0!
6 | DOTCOM | Yamini | #DIV/0!
7 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 100% | 76 | 76 | 0 | 0 | 160 | A1
8 | RTP Normal Scenarios | Ramya | 92.59% | 162 | 150 | 10 | 2 | 393 | A1 | no run- ALM update null pointer exception. 10 - Got order source invalid error. Missing service address
9 | Handle_Invalidservices | Ashwini | 76.92% | 13 | 10 | 3 | 0 | 181 | A1 | Not able to find rootcause. Got 100% when we kicked off via parasoft. 1st time issue | working on to find root cause
10 | Release_From_ThirtyDay_All | Yamini | 66.67% | 15 | 10 | 5 | 0 | 322 | A4 | 1 scenario-Intermittent Issue: Status became completed 2 scenario- Environmet slowness- difference detween disconnect calls and processhomesecurity is 25 sec wherein we have given 5 sec in script. 2 scenarios: Intermittent Issue- Simulator didn’t turn ON so it went to cancel
11 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 92.86% | 28 | 26 | 2 | 0 | 56 | A2 | 1 scenario -Environment slowness, differences between createCMSAccountId and OrderUpdate is 35 sec. 1 scenario - createAccount No response.
12 | JasperAfterCOS_ResumeFlowAddition | Ramya | 86.21% | 29 | 25 | 4 | 0 | 43 | A2 | RJ error | NA
13 | Cancel_ON_Disconnect | Ashwini | 94.34% | 53 | 50 | 3 | 0 | 84 | A2 | 1- only event call triggered 2-not able to fetch calls on time | NA
14 | Handle_Invalid Services with Virtualize | Ashwini | 86.21% | 29 | 25 | 4 | 0 | 72 | A2 | null pointer exception | Working on this issue.
15 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 100% | 23 | 23 | 0 | 0 | 34 | A2
16 | RTP_Upgrade and downgrade | Bhuvana | 80.95% | 42 | 34 | 8 | 0 | 235 | A2 | COPS no response | NA
17 | 30Day Disconnect | Yamini | 91.25% | 80 | 73 | 6 | 1 | 203 | A2 | 5 scenarios failed - Environment slowness. We have given time difference between createcmsaccount and orderupdate is 29 sec. But this exceeds from 30 sec to 1 min 1 scenario- create account no response
18 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 49 | A4
| Total |  | 92.81% | 668 | 620 | 45 | 3

## Dec22
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VM | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | 91.67% | 12 | 11 | 1 | 0 | 20 | A5 | Latency issue | NA.. Passed, post re-run
2 | Comtrac_All | Ramya | 100% | 18 | 18 | 0 | 0 | 19 | A5
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 | 5 | A5
4 | DTA | Ramya | 28.57% | 7 | 2 | 5 | 0 | 24 | A5 | Account number went as different . | Need to change the account number and monitor
5 | SwivelCSG | Ashwini | 100% | 55 | 55 | 0 | 0 | 29 | A5
6 | DOTCOM | Yamini | 94.23% | 52 | 49 | 3 | 0 | 125 | A5 | Latency issue | NA
7 | SIKNegativeCases | Bhuvana | 80% | 5 | 4 | 0 | 1 | 55 | A5 | test set ID issue | modified test set ID and passed, post re-run
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 94.74% | 76 | 72 | 4 | 0 | 194 | A1 | String index out of bound exception, only if we kick off via Jenkins (I,e while running all jobs parallely). Kicked off job again with only one tst via Jenkins and I am not facing this string index out of bound exception. | Passes, post re-run
9 | RTP Normal Scenarios | Ramya | 90.74% | 162 | 147 | 13 | 2 | 497 | A1 | 1 New install failed cz createCMS Failed. 2 COS Failed cz of this 1 Suspend, 1 Restore and 1 Cancel failed. Remaining 7 are CVR Related. Need to check with Yamini | 2 ALM Updated threw null pointer exception. Need to monitor
10 | Handle_Invalidservices | Ashwini | 84.62% | 13 | 11 | 2 | 0 | 165 | A1 | RJ error followed byCOS failure | NA
11 | Release_From_ThirtyDay_All | Yamini | 53.33% | 15 | 8 | 7 | 0 | 313 | A4 | Intermittent Issues:: Status updated as Completed instead of open.
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 100% | 28 | 28 | 0 | 0 | 56 | A2
13 | JasperAfterCOS_ResumeFlowAddition | Ramya | 79.31% | 29 | 23 | 6 | 0 | 44 | A2 | All failed due to RJ Error
14 | Cancel_ON_Disconnect | Ashwini | 100% | 53 | 53 | 0 | 0 | 82 | A2
15 | Handle_Invalid Services with Virtualize | Ashwini | 89.66% | 29 | 26 | 3 | 0 | 72 | A2 | Null pointer exception | Fix required
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 100% | 23 | 23 | 0 | 0 | 64 | A2
17 | RTP_Upgrade and downgrade | Bhuvana | 80.95% | 42 | 34 | 8 | 0 | 233 | A2 | RJ error | NA
18 | 30Day Disconnect | Yamini | 95% | 80 | 76 | 3 | 1 | 1 | A2 | Environment slowness | NA
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 49 | A4
| Total |  | 92.85% | 825 | 766 | 55 | 4

## Jan13
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VDI | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | 91.67% | 12 | 11 | 1 | 0 | 21 | 4 | Latency issue | re-run and it got passed
2 | Comtrac_All | Ramya | 100% | 18 | 18 | 0 | 0 | 20 | 4
3 | CustomerMoves | Bhuvana | 75% | 8 | 6 | 2 | 0 | 5 | 4 | Latency issue | re-run and it got passed
4 | DTA | Ramya | 85.71% | 7 | 6 | 1 | 0 | 24 | 4 | Not able to track issue because FTA validation is getting failed only via batch. | Need to check root cause.
5 | SwivelCSG | Ashwini | 100% | 55 | 55 | 0 | 0 | 32 | 4
6 | DOTCOM | Yamini | 92.31% | 52 | 48 | 3 | 1 | 129 | 4 | In 3 test cases, script could not capture from querycontract calls eventhough timing is proper. When I ran separately, it is going fine. Not sure ,going forward will be monitoring. No Run- no test cases in NoRun | re-run and it got passed
7 | SIKNegativeCases | Bhuvana | 0% | 5 | 0 | 0 | 5 | 1 | 4 | wrong path configuration, so job didn’t kick off. | re-run job and all test case got passed, but we could not able to find test cases in OCR folder
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 94.74% | 76 | 72 | 4 | 0 | 226 | 1 | String index out of bound exception, only if we kick off via Jenkins (I,e while running all jobs parallely). Kicked off job again with only one tst via Jenkins and I am not facing this string index out of bound exception. | re-run and it got passed. Need to change configuration in Jenkins and check.
9 | RTP Normal Scenarios | Ramya | 54.94% | 162 | 89 | 73 | 0 | 394 | 1 | Latency issue for All CSG Normal scenarios and Release B failued due to Configurations miss | Configurations should be reverted back once testing done
10 | Handle_Invalidservices | Ashwini | 7.692% | 13 | 1 | 0 | 12 | 0 | 1 | Unable to run through batch | Did all modifications in all 4 vdI and it is working fine now
11 | Release_From_ThirtyDay_All | Yamini | 73.33% | 15 | 11 | 4 | 0 | 313 | 3 | 2 failed- Intermittent issue COPS failed even though install was success.(re-run and it got passed) 2 failed- Environment Slowness. | Going forward, if this continues for more scenarios, will be giving more think time
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 96.43% | 28 | 27 | 1 | 0 | 60 | 2 | Failure-1 – Environment slowness ( Order update has come after 40 sec from createCMSAccountID) | Going forward, if this continues for more scenarios, will be giving more think time
13 | JasperAfterCOS_ResumeFlowAddition | Ramya | 100% | 29 | 29 | 0 | 0 | 46 | 2
14 | Cancel_ON_Disconnect | Ashwini | 100% | 53 | 53 | 0 | 0 | 87 | 2
15 | Handle_Invalid Services with Virtualize | Ashwini | 51.72% | 29 | 15 | 0 | 14 | 75 | 2 | Unable to run through batch | Did all modifications in all 4 vdI and it is working fine now
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 60.87% | 23 | 14 | 3 | 6 | 47 | 2 | schedule update table was not updated and hence we got null pointer exception. | re-run job and test cases got passed.
17 | RTP_Upgrade and downgrade | Bhuvana | 92.86% | 42 | 39 | 3 | 0 | 239 | 2 | Latency issue | re-run job and it got passed
18 | 30Day Disconnect | Yamini | 96.25% | 80 | 77 | 2 | 1 | 209 | 2 | Failure 2- Intermittent issue, Release B scenarios-flows didn’t go completely, it stopped in xhsevent. Now the flows are going properly, No run-1 (Positive ALM null pointer exception) | Re-ran test cases and it is working as expected.
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 49 | 3
| Total |  | 83.52% | 825 | 689 | 97 | 39

## Jan21
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VDI | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | #DIV/0! |  |  |  |  | 21 | 4
2 | Comtrac_All | Ramya | #DIV/0! |  |  |  |  | 20 | 4
3 | CustomerMoves | Bhuvana | #DIV/0! |  |  |  |  | 5 | 4
4 | DTA | Ramya | #DIV/0! |  |  |  |  | 24 | 4
5 | SwivelCSG | Ashwini | #DIV/0! |  |  |  |  | 32 | 4
6 | DOTCOM | Yamini | #DIV/0! |  |  |  |  | 129 | 4
7 | SIKNegativeCases | Bhuvana | #DIV/0! |  |  |  |  | 1 | 4
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 97.37% | 76 | 74 | 2 |  | 226 | 1
9 | RTP Normal Scenarios | Tejasvi | 75.93% | 162 | 123 | 39 | 0 | 394 | 1 | 19 scenarios failed due to orderSource validation CVR scenarios-15 failed getAccount no response-5 scenarios
10 | Handle_Invalidservices | Ashwini | 84.62% | 13 | 11 | 2 | 0 | 0 | 1 |  | Re Ran and it is working fine
11 | Release_From_ThirtyDay_All | Yamini | 73.33% | 15 | 11 | 4 | 0 | 313 | 3 | Intermittent Issue: scenarios went to cancel even status as Active. | Re-ran and it is working as expected.
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 100% | 28 | 28 | 0 | 0 | 60 | 2
13 | JasperAfterCOS_ResumeFlowAddition | Tejasvi | 86.21% | 29 | 25 | 4 |  | 46 | 2 | DDS no response
14 | Cancel_ON_Disconnect | Ashwini | 84.91% | 53 | 45 | 8 | 0 | 87 | 2 | Msg Id's were not picked , need to monitor it next time
15 | Handle_Invalid Services with Virtualize | Ashwini | 93.1% | 29 | 27 | 2 |  | 75 | 2 |  | Re Ran and it is working fine
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 0% | 23 | 0 | 0 | 23 | 47 | 2 | Batch dint run. "The system cannot find the path specified" error in report
17 | RTP_Upgrade and downgrade | Bhuvana | 80.95% | 42 | 34 | 8 | 0 | 239 | 2 | RJ error, Account already exists error from createAccount | NA
18 | 30Day Disconnect | Yamini | 88.75% | 80 | 71 | 7 | 2 | 209 | 2 | 4 failed-9992050388771,9992050388999,9992050364759,9992050364970-Ucontrol was Down 3 failed- Virtualize getaccount went as no response as process was running in between. 2 No Run-Positive null pointer exception | Re-ran and it is working as expected.
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 49 | 3
| Total |  | 84.88% | 668 | 567 | 76 | 25

## Jan25
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VDI | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | 91.67% | 12 | 11 | 1 | 0 | 21 | 4 | Latency Issue
2 | Comtrac_All | Teju | 100% | 18 | 18 | 0 | 0 | 19 | 4
3 | CustomerMoves | Bhuvana | 75% | 8 | 6 | 2 | 0 | 5 | 4 | Latency Issue: (diff 55 sec in Order Update)
4 | DTA | Teju | 85.71% | 7 | 6 | 1 | 0 | 24 | 4 | Latency Issue
5 | SwivelCSG | Ashwini | 93.22% | 59 | 55 | 0 | 4 | 31 | 4
6 | DOTCOM | Yamini | 94.23% | 52 | 49 | 3 | 0 | 128 | 4 | 3 failed whereas script could nt capture call on time. Not sure, environment was good. but flows are going properly and succeeded. | Will be monitoring this.
7 | SIKNegativeCases | Bhuvana | 0% | 29 | 0 | 0 | 29 | 4 | 4 | File path is wrong. It is configured as C:\OCR_fix_tst\SIKNegativeCases\parameterList_Dotcom.xlsx (The system cannot find the path specified) As per VDI, we have to configure as C:\OP_Regression folder. | configured correct path.
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 93.33% | 90 | 84 | 6 | 0 | 213 | 1 | 3 scenarios - Account number issue. Account already exists so install failed. 3 scenarios - ORDER Update throws an error as Invalid service since foxtrot was enabled. | Please fix the 100TDPEV script .
9 | RTP Normal Scenarios | Teju | 43.55% | 248 | 108 | 49 | 91 | 498 | 1 | CVR cases failed due to delayed response time. DDP Normal RTP- Test Data issue- due to which Geodtic call's failed DDP-Release B cases failed due to HHS down No RUN- observed this issue as intermittent issue. When ran via parasoft working as expected | Re ran cases, working fine. DDP Normal RTP- changed Test data.
10 | Handle_Invalidservices | Ashwini | 0% | 13 | 0 | 0 | 13 | 1 | 1 | Batch file dint run got below error: C:\OP_Regression\Handle_Invalidservices\Handle_InvalidServices\Handle_InvalidServices\Input\XMLParameter_New_DDP_HandleInvalidService_without simulator.xlsx (The system cannot find the path specified)
11 | Release_From_ThirtyDay_All | Yamini | 46.67% | 15 | 7 | 8 | 0 | 241 | 3 | Environment Slowness: we have given time diff between createCMSAccountId and OrderUpdate is 25 sec in script. 9992050305189- Time exceeds to 1 min 10 sec from Environment Slowness:createCMSAccountId to OrderUpdate. 9992050305289-diff (1 min 5 sec) 9992050305389-diff (1 min 20 sec) 8720101017056678-diff (2 min 20 sec) 8720101017056689-diff(3 mins) 8720101017056668-diff(3 mins) 8720101017056678-diff(2 mins) 9992050311598-diff(2 mins)
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 72.5% | 40 | 29 | 1 | 10 | 60 | 2 | CLS configurations are there in QA4. So UContorl suspend Account went as CLS suspend Account,so script Validation failed. | please make sure before kick off OCR whether all configurations are disabled.
13 | JasperAfterCOS_ResumeFlowAddition | Teju | 86.21% | 29 | 25 | 4 | 0 | 47 | 2 | CLS configurations were present in UI | cleared CLS configurations in QA4
14 | Cancel_ON_Disconnect | Ashwini | 42.86% | 56 | 24 | 31 | 1 | 86 | 2 | CLS configurations were present in UI | cleared CLS configurations in QA4
15 | Handle_Invalid Services with Virtualize | Ashwini | 100% | 24 | 24 | 0 | 0 | 75 | 2
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 50% | 48 | 24 | 3 | 21 | 127 | 2 | 15 No Run test cases belongs to CVR schedule UP/down wherein newly updated excel file is not updated in SVN,so testcases id s are not mapped so it leads to No run. | Updated the new sheet and validated the calls whereas flows are working as expected.
17 | RTP_Upgrade and downgrade | Bhuvana | 40% | 45 | 18 | 13 | 14 | 238 | 2 | 1) Soap Parameterization was wrong so it is not processing cancel request. 2) Because of this accounts are not getting cancelled. So next time when we are running, it is throwing account already exists error. 3)11 scenarios failed-account already exists(which didnt cancelled ) 4) Norun cases - not sure these cases didnt run only. | Fixed the soap parameterization.
18 | 30Day Disconnect | Yamini | 92.39% | 92 | 85 | 6 | 1 | 242 | 2 | 5 scenario-9992050388999-(diff is 36 sec) 1 scenario- Intermittent Issue (uNCONTROL went DOWN) | Flows are working as expected in UI.
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 56 | 3
| Total |  | 68.89% | 1003 | 691 | 128 | 184

## Feb4
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VDI | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | 100% | 12 | 12 | 0 | 0 | 21 | 4
2 | Comtrac_All | Teju | 100% | 18 | 18 | 0 | 0 | 21 | 4
3 | CustomerMoves | Bhuvana | 75% | 8 | 6 | 2 | 0 | 5 | 4 | CSG Account issue- Account equipment was not present. Replaced with new account, working fine now | Need to create backup account for such cases.
4 | DTA | Teju | 100% | 7 | 7 | 0 | 0 | 24 | 4
5 | SwivelCSG | Ashwini | 94.92% | 59 | 56 | 0 | 3 | 31 | 4 | There were no failure in ALM- 100% passed
6 | DOTCOM | Yamini | 100% | 52 | 52 | 0 | 0 | 129 | 4
7 | SIKNegativeCases | Bhuvana | 100% | 29 | 29 | 0 | 0 | 54 | 4
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 98.89% | 90 | 89 | 1 | 0 | 217 | 1 | No response from getAccount | NA
9 | RTP Normal Scenarios | Teju | 85.08% | 248 | 211 | 3 | 34 | 497 | 1 | 34- NORUN cases are CLS related TC's. 1CVR case failed due to delayed DDS response geodeticQuery- call null response | Intermittent issue, while re-executing again functionality is working as expected.
10 | Handle_Invalidservices | Ashwini | 100% | 13 | 13 | 0 | 0 | 226 | 1
11 | Release_From_ThirtyDay_All | Yamini | 66.67% | 15 | 10 | 5 | 0 | 390 | 3 | Intermittent Issue: 1 scenario- Status went as Completed instead of open. 1 scenario- Jasper status went as "DEACTIVATED-NAME" instead of "RETIRED_NAME". Environment Slowness: 3 scenario: we have given time diff between createCMSAccountId and OrderUpdate is 25 sec in script. ex: 8720101017054777-45 sec from CMS to Order Update | Intermittent issue, while re-executing again functionality is working as expected. Environment slowness, we are planning to apply dynamic way of handling think time logic in between createcmsaccountId call and order update call but in this present OCR while checking functionality it working as expected.
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 97.5% | 40 | 39 | 1 | 0 | 60 | 2 | Environment Slowness: we have given time diff between createCMSAccountId and OrderUpdate is 13 sec in script. Since it exceeds to 37 sec , scriptcouldn't capture on time. So 1 scenario failed. Acc: 8720101010090799 | Environment slowness, we are planning to apply dynamic way of handling think time logic in between createcmsaccountId call and order update call but in this present OCR while checking functionality it working as expected.
13 | JasperAfterCOS_ResumeFlowAddition | Teju | 96.55% | 29 | 28 | 1 | 0 | 48 | 2 | Delayed Order update call, hence orderUpdate validations are failed re-Ran rest -It is working fine | NA
14 | Cancel_ON_Disconnect | Ashwini | 100% | 56 | 56 | 0 | 0 | 86 | 2
15 | Handle_Invalid Services with Virtualize | Ashwini | 93.1% | 29 | 27 | 2 | 0 | 76 | 2 | Re-Ran it is working fine
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 83.33% | 48 | 40 | 5 | 3 | 144 | 2 | Intermittent Issue: 2 scenario- Status went as Completed instead of open.Not sure some process might have run in between. 3 scenarios cvr- Table validation went to null pointer exception.Releases from table might have taken some time to get release. No Run: 3-Update ALM pass null pointer exception. | Intermittent issue, while re-executing again functionality is working as expected.
17 | RTP_Upgrade and downgrade | Bhuvana | 77.78% | 45 | 35 | 10 | 0 | 238 | 2 | Order update was triggered after 1 min-1 scenario re-Ran rest -It is working fine | NA
18 | 30Day Disconnect | Yamini | 58.7% | 92 | 54 | 37 | 1 | 226 | 2 | Environment slowness: No of scenarios :36 Example: 9992050389993--43 sec from CMS to OU. 9992050389999-43 sec from CMS to OU. 8720101017052564-44 sec 9992050364759-44 sec Ucontrol service went down: No of scenarios:1 8720101017052562- Intrado no res No Run: Null pointer Exception | Intermittent issue, while re-executing again functionality is working as expected. Environment slowness, we are planning to apply dynamic way of handling think time logic in between createcmsaccountId call and order update call but in this present OCR while checking functionality it working as expected.
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 59 | 3
| Total |  | 89.29% | 1008 | 900 | 67 | 41

## Feb9
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VDI | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | 100% | 12 | 12 | 0 | 0 | 20 | 4
2 | Comtrac_All | Teju | 100% | 18 | 18 | 0 | 0 | 20 | 4
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 | 5 | 4
4 | DTA | Teju | 100% | 7 | 7 | 0 | 0 | 24 | 4
5 | SwivelCSG | Ashwini | 61.02% | 59 | 36 | 19 | 4 | 30 | 4
6 | DOTCOM | Yamini | 100% | 52 | 52 | 0 | 0 | 127 | 4
7 | SIKNegativeCases | Bhuvana | 17.24% | 29 | 5 | 8 | 16 | 45 | 4
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 96.67% | 90 | 87 | 3 | 0 | 217 | 1
9 | RTP Normal Scenarios | Teju | 27.02% | 248 | 67 | 162 | 19 | 624 | 1
10 | Handle_Invalidservices | Ashwini | 100% | 13 | 13 | 0 | 0 | 194 | 1
11 | Release_From_ThirtyDay_All | Yamini | 66.67% | 15 | 10 | 5 | 0 | 300 | 3
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 47.5% | 40 | 19 | 21 | 0 | 59 | 2
13 | JasperAfterCOS_ResumeFlowAddition | Teju | 100% | 29 | 29 | 0 | 0 | 46 | 2
14 | Cancel_ON_Disconnect | Ashwini | 91.07% | 56 | 51 | 5 | 0 | 85 | 2
15 | Handle_Invalid Services with Virtualize | Ashwini | 96.55% | 29 | 28 | 0 | 1 | 73 | 2
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 14.58% | 48 | 7 | 26 | 15 | 148 | 2
17 | RTP_Upgrade and downgrade | Bhuvana | 0% | 45 | 0 | 45 | 0 | 242 | 2
18 | 30Day Disconnect | Yamini | 65.22% | 92 | 60 | 31 | 1 | 240 | 2
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 60 | 3
| Total |  | 62.2% | 1008 | 627 | 325 | 56

## Mar6
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VDI | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | 50% | 12 | 6 | 6 | 0 | 21 | 4 | SIK OMS Intermitent issue | Re-Ran and updated ALM
2 | Comtrac_All | Teju | 38.89% | 18 | 7 | 11 | 0 | 20 | 4 | SIK OMS Intermitent issue | Re-Ran and updated ALM
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 | 5 | 4 | SIK OMS Intermitent issue | Re-Ran and updated ALM
4 | DTA | Teju | 0% | 7 | 0 | 7 | 0 | 23 | 4 | SIK OMS Intermitent issue | Re-Ran and updated ALM
5 | SwivelCSG | Ashwini | 5.085% | 59 | 3 | 52 | 4 | 36 | 4 | SIK OMS Intermitent issue | Re-Ran and updated ALM
6 | DOTCOM | Yamini | 17.31% | 52 | 9 | 42 | 1 | 136 | 4 | No run-Alm connection refused, Failed scenarios-SIKOMS intermitent issue | Re-Ran and updated ALM
7 | SIKNegativeCases | Bhuvana | 31.03% | 29 | 9 | 18 | 2 | 59 | 4 | No run-Alm connection refused, Failed scenarios-SIKOMS intermitent issue | Re-Ran and updated ALM
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 33.33% | 90 | 30 | 60 | 0 | 220 | 3 | There was 60 min delay in calls. Seeing this for first time | Need to monitor this issue
9 | RTP Normal Scenarios | Teju | 90.72% | 194 | 176 | 9 | 9 | 627 | 3 | No Run-Alm connectivity issue Failure due to intermitent environment slowness
10 | Handle_Invalidservices | Ashwini | 0% | 12 | 0 | 0 | 12 | 0 | 3 | Batch dint run. Job | Ran Batch seperately it was working fine.
11 | Release_From_ThirtyDay_All | Yamini | 33.33% | 15 | 5 | 9 | 1 | 298 | 1 | We have observed Jasper geTerminaldetails call status is not consistent. So script is failing. | We communicated to DEV Team. Once behaviour is confirmed, we 'll provide fix in script according to that.
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 87.5% | 40 | 35 | 5 | 0 | 65 | 2 | COPS went down setAccountAuthorityInformation call throws no response | Re-Ran and updated ALM
13 | JasperAfterCOS_ResumeFlowAddition | Teju | 100% | 29 | 29 | 0 | 0 | 63 | 2
14 | Cancel_ON_Disconnect | Ashwini | 96.43% | 56 | 54 | 2 | 0 | 86 | 2 | Calls got delayed . There was 4 sec gap between getAccount and quiery location call . Script waited for 2 sec.- 2 scenarios failed | re-Ran it is working fine
15 | Handle_Invalid Services with Virtualize | Ashwini | 100% | 17 | 17 | 0 | 0 | 75 | 2
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 50% | 48 | 24 | 2 | 22 | 194 | 2 | No run-Alm connection refused Failed Scenarios-Got RJ error | Cleaned up Account number
17 | RTP_Upgrade and downgrade | Bhuvana | 71.11% | 45 | 32 | 13 | 0 | 226 | 2 | 6 scenarios. There was 15 Sec delay in calls. suspendAccount and SetAccountBasicInformation during downgrade 6 scenarios- RJ error . | We need to implement dynamic way of handling think time
18 | 30Day Disconnect | Yamini | 93.48% | 92 | 86 | 5 | 0 | 231 | 2 | 5 scenarios- DDS was down
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 118 | 1
| Total |  | 68.86% | 941 | 648 | 241 | 51

## Mar24
SL.No | tst file | Owner | Batch Run Status(Pass %) | Total Test Cases Run | Passed | Failed | No Run | Time Taken for complete run(In Mins) | VDI | Failure Reason(Test Case Wise) | What action taken to fix?
1 | Multiple_Product_Component | Bhuvana | 66.67% | 12 | 8 | 4 | 0 | 20 | 4
2 | Comtrac_All | Teju | 55.56% | 18 | 10 | 8 | 0 | 20 | 4
3 | CustomerMoves | Bhuvana | 100% | 8 | 8 | 0 | 0 | 5 | 4
4 | DTA | Teju | 0% | 7 | 0 | 7 | 0 | 24 | 4
5 | SwivelCSG | Ashwini | 57.63% | 59 | 34 | 21 | 4 | 30 | 4 | End point configured to cancel order ID was wrong | Corrected and RE-RAN
6 | DOTCOM | Yamini | 26.92% | 52 | 14 | 37 | 1 | 127 | 4 | Functionality Issue:: Submit order throws product code issue for the corp "99920" and it is worklisting. We raised defect. | Issue has been resolved. We re-executed and confirmed functionality is working as expected.
7 | SIKNegativeCases | Bhuvana | 34.48% | 29 | 10 | 18 | 1 | 58 | 4
8 | DDP_CSG_Install+COS+Suspend+Restore+Cancel_Insight | Bhuvana | 31.08% | 74 | 23 | 51 | 0 | 177 | 1 | 3 scenarios failed due to install was failure{simulator was on} 100EVTDP-failed as invalid scenario-6 scenarios,DDS service down-5 scenarios. Environment slowness-12scenarios | Re-Ran remaining scenarios and found no issues.
9 | RTP Normal Scenarios | Teju | 47.98% | 198 | 95 | 82 | 21 | 660 | 1
10 | Handle_Invalidservices | Ashwini | 100% | 13 | 13 | 0 | 0 | 175 | 1
11 | Release_From_ThirtyDay_All | Yamini | 46.67% | 15 | 7 | 8 | 0 | 314 | 3 | Environment Issue : No of scenarios failed-4 Intrado No response-because of this Install didn’t happen properly which leads to RJ error Intermittent Issues: No of scenarios failed-1: Status went as completed instead of open so Validation failed Environment slowness: No of scenarios failed:3 COPS and DDS exceeds the assigned time in the script | We started working on applying dynamic think time. We re-executed failed cases and flows are going fine.
12 | Cancel_Change_and_Cancel_Disconnect_sus_and_Res_check | Yamini | 95% | 40 | 38 | 2 | 0 | 53 | 2 | Configuration Issue: In sql DB, service was updated as 300 instead of 300EV since we changed the service recently. | We updated service as 300EV in SQL DB and re-excuted two cases and it is working as expected.
13 | JasperAfterCOS_ResumeFlowAddition | Teju | 62.07% | 29 | 18 | 6 | 5 | 43 | 2
14 | Cancel_ON_Disconnect | Ashwini | 100% | 37 | 37 | 0 | 0 | 77 | 2
15 | Handle_Invalid Services with Virtualize | Ashwini | 100% | 29 | 29 | 0 | 0 | 74 | 2
16 | SCHEDULE_UPGRADE_DOWNGRADE | Bhuvana | 38.89% | 18 | 7 | 9 | 2 | 144 | 2
17 | RTP_Upgrade and downgrade | Bhuvana | 28.57% | 35 | 10 | 25 | 0 | 155 | 2 | Cops was down- 20 scenarios , RJ error-5 | NA
18 | 30Day Disconnect | Yamini | 77.17% | 92 | 71 | 21 | 0 | 229 | 2 | Intermittent Issue: COPS service was down. | We re-executed failed cases and flows are going fine.
19 | IgnoreworklistRTP | Yamini | 100% | 118 | 118 | 0 | 0 | 61 | 3
| Total |  | 62.29% | 883 | 550 | 299 | 34